## Introduction
Scrum Master User One
Developer Prajjwol Upadhayaya
Developer Ram Khatri
Developer Hari Acharya
Developer Bishnu Adhikari
Developer Shrawan Thapa
MyPalBooks
(Online Bookstore)

## User Story Without Priority
LIST OF USER STORIES
S.N. | User Story | Acceptance Criteria
1 | As a user, I need to register to the system by creating an account, so that I can use the system. | • Add register button in the navigation bar of the system. • Display the registration form when the button is clicked. • Provide all the required fields with proper validation. • Finally, click the register button placed in the form for creating the account.
2 | As a user, I need to be notified via an email verification mail to my email address, so that I can verify my account after registration. | • Send an email verification link to registered email address of the user. • Click the verification link attached with email for account verification. • Verification link expires after 24 hours. • Once verified link cannot be reused.
3 | As a user, I need to login to the system after registration, so that I can access the system. | • Add a login button in the navigation bar of the system. • Display the login form when the button is clicked. • Provide login credentials to the required fields with validation. • Ultimately, click the login button for accessing the system. • Display the dashboard page after successful login.
4 | As a user, I need to reset my forgotten password, so that I can create a new one to access the system. | • Add a forget password button on login page. • Click the placed button. • Display the form for resetting the password. • Accept valid and registered email of user in the form and submit it. • Send a password reset link to the provided email address. • Click the reset link attached with email for resetting the password. • Access the password reset form in the browser and provide the new password. • Ultimately, click the button placed in the form for resetting the password with the new one. • Reset link expires after 24 hours. • Once verified link cannot be reused.
5 | As a user, I need to change my password used during login, so that I can secure my account. | • Add change password link on profile section of the user dashboard. • Click the link to access the change password form. • Ask for old password and accept to enter new password with proper validation. • Once the old password is verified the password should change successfully. • Click the button placed in the form for changing the password. • Clear the session of the logged in user after successful password change. • Redirect to the login page for continuing with new password.
6 | As user, I need to add a profile picture, so that I could get recognized by other people. | • Add choose profile picture option on the profile section of the dashboard. • Ask to choose the file and browse the file explorer. • Choose the appropriate picture and upload it. • Click the upload button to add the selected image as profile picture.
7 | As a user, I need to see my activity logs in the system, so that I can track my activities in the system. | • Add a ‘Activity Logs’ link in the navigation bar of the dashboard. • Click the link and browse a new section in the dashboard. • View all the activities done by the logged in user in that section.
8 | As a user, I need to login to the system using third party OAuth, so that I can access the system securely with a single click. | • Add continue with (Google, Facebook) option in the login form of the system. • Click the relevant option for continuing the system login. • Select the appropriate account to continue with the system. • Click the selected account and login to the system with single click. • Access the system’s dashboard after successful login. • Sync and monitor user activities via the host account service provider.
9 | As a user, I need to explore the various kinds of available books, so that I can look for the one of my choice. | • Access the home page of the system where all the books are presented. • Display a section in the page where the information about various books are presented and updated. • Select and go through the section for viewing the information presented about various books. • Compare the presented information of various books with each other.
10 | As a user, I need to search for a book of my choice, so that I can know about it in more detail. | • Add a search button in the navigation bar of the system. • Provide the search tag of interested book (date of publish, genre, name, etc.) and click the search button. • Display the relevant data based upon the search filter provided and go through it.
11 | As a user, I need to view a book of my choice in detail, so that I can figure out its price, writer, comments, ratings and other detailed information. | • Access the home page of the system where all the information is presented. • Display a section in the page where the information about various books are presented and updated. • Select and go through the section to view the information presented about different books or search the book of choice using the search box placed in the navigation bar by providing essential search filters. • Browse the book of choice and go through it. • View the detailed information about the book.
12 | As a user, I need to add comment to the book I viewed, so that I can present my views regarding it in public. | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a comment section below the book description. • Present all the views and thoughts regarding that book in the section. • Click the add button to add the comment and make it publicly visible.
13 | As a user, I need to give rating for a book I viewed, so that I can express my reaction towards it. | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a rating bar next to the comment section below the book description. • Express the reaction towards that book by rating it via that rating bar. • After rating it will be publicly visible.
14 | As a user, I need to buy a book of my choice, so that I can read it. | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a buy button next to the add comment button. • Click the button to initate the purchase. • Select the desired payment method and continue to pay.
15 | As a user, I need to add a book to favourites, so that I can view it later. | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Add to Favourites' button next to the book image. • Click the button to add book to favourites. • Browse the favourites section to see the added book as favourites.
16 | As a user, I need to add a book to the system, so that other users can go through it and carryout relevant activites. | • Add 'Upload a Book' link on navigation bar of the dashboard. • Click the link to access the upload a book form. • Ask for various details of book to upload with proper validation. • Click the 'Add' button placed in the form for adding book to the system. • Redirect to the 'MyBooks' section after adding book successfully.
17 | As a user, I need to review my books, so that I can see its booking transactions and other information. | • Access and go through the 'MyBooks' section in the dashboard. • Display all the books hosted by a user. • Click on a book to view its booking details, reviews and ratings. • Review the information to perform various activites.
18 | As a user, I need to update the details of book I uploaded, so that other users can view latest information regarding it. | • Access and go through the 'MyBooks' section in the dashboard. • Display all the books hosted by a user. • Click on a book to update and access the update form. • Provide new information and click the 'Update' button to update the book.
19 | As a user, I need to deactivate my account, so that I can safeguard my privacy. | • Add account deactivate button in the profile section. • Click the button to disable their account temporarily or permanently. • Once the account is deactivated it should not be visible in the system. • Clear the session of the user after successful account deactivation.
20 | As a user, I need to share a book in other social platforms, so that user of other social medias can also view it. | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Share' button next to the 'Add to Favourites' button. • Click the button to access the modal with hyperlink of the book. • Copy the hyperlink and share it in other social medias.

## Agile User Story
AGILE USER STORY
Feature ID | Feature Name | User Story ID | Priority | As a <Type of user> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria
F1 | User Account | 1.1 | High | User | register to the system by creating an account | use the system. | • Add register button in the navigation bar of the system. • Display the registration form when the button is clicked. • Provide all the required fields with proper validation. • Finally, click the register button placed in the form for creating the account.
|  | 1.2 | High | User | be notified via an email verification mail to my email address | I can verify my account after registration. | • Send an email verification link to registered email address of the user. • Click the verification link attached with email for account verification. • Verification link expires after 24 hours. • Once verified link cannot be reused.
|  | 1.3 | High | User | login to the system after registration | I can access the system | • Add a login button in the navigation bar of the system. • Display the login form when the button is clicked. • Provide login credentials to the required fields with validation. • Ultimately, click the login button for accessing the system. • Display the dashboard page after successful login.
|  | 1.4 | Low | User | login to the system using third party OAuth | I can access the system securely with a single click. | • Add continue with (Google, Facebook) option in the login form of the system. • Click the relevant option for continuing the system login. • Select the appropriate account to continue with the system. • Click the selected account and login to the system with single click. • Access the system’s user dashboard after successful login. • Sync and monitor user activities via the host account service provider.
|  | 1.5 | High | User | reset my forgotten password | I can create a new one to access the system | • Add a forget password button on login page. • Click the placed button. • Display the form for resetting the password. • Accept valid and registered email of user in the form and submit it. • Send a password reset link to the provided email address. • Click the reset link attached with email for resetting the password. • Access the password reset form in the browser and provide the new password. • Ultimately, click the button placed in the form for resetting the password with the new one. • Reset link expires after 24 hours. • Once verified link cannot be reused.
|  | 1.6 | Medium | User | change my password used during login | I can secure my account. | • Add change password link on profile section of the user dashboard. • Click the link to access the change password form. • Ask for old password and accept to enter new password with proper validation. • Once the old password is verified the password should change successfully. • Click the button placed in the form for changing the password. • Clear the session of the logged in user after successful password change. • Redirect to the login page for continuing with new password.
F2 | Dashboard | 2.1 | Medium | User | add a profile picture | I could get recognized by other people. | • Add choose profile picture option on the profile section of the dashboard. • Ask to choose the file and browse the file explorer. • Choose the appropriate picture and upload it. • Click the upload button to add the selected image as profile picture.
|  | 2.2 | Low | User | see my activity logs in the system | I can track my activities in the system. | • Add a ‘Activity Logs’ link in the navigation bar of the dashboard. • Click the link and browse a new section in the dashboard. • View all the activities done by the logged in user in that section.
|  | 2.3 | High | User | add a book to the system | other users can go through it and carryout relevant activities | • Add 'Upload a Book' link on navigation bar of the dashboard. • Click the link to access the upload a book form. • Ask for various details of book to upload with proper validation. • Click the 'Add' button placed in the form for adding book to the system. • Redirect to the 'MyBooks' section after adding book successfully.
|  | 2.4 | High | User | review my books | I can see its booking transactions and other information | • Access and go through the 'MyBooks' section in the dashboard. • Display all the books hosted by a user. • Click on a book to view its booking details, reviews and ratings. • Review the information to perform various activites.
|  | 2.5 | High | User | update the details of book I uploaded | other users can view latest information regarding it | • Access and go through the 'MyBooks' section in the dashboard. • Display all the books hosted by a user. • Click on a book to update and access the update form. • Provide new information and click the 'Update' button to update the book.
|  | 2.6 | Low | User | deactivate my account | I can safeguard my privacy. | • Add account deactivate button in the profile section. • Click the button to disable their account temporarily or permanently. • Once the account is deactivated it should not be visible in the system. • Clear the session of the user after successful account deactivation.
F3 | Viewing | 3.1 | High | User | explore the various kinds of available books | I can look for the one of my choice | • Access the home page of the system where all the books are presented. • Display a section in the page where the information about various books are presented and updated. • Select and go through the section for viewing the information presented about various books. • Compare the presented information of various books with each other.
|  | 3.2 | High | User | view a book of my choice in detail | I can figure out its price, writer, comments, ratings and other detailed information | • Access the home page of the system where all the information is presented. • Display a section in the page where the information about various books are presented and updated. • Select and go through the section to view the information presented about different books or search the book of choice using the search box placed in the navigation bar by providing essential search filters. • Browse the book of choice and go through it. • View the detailed information about the book.
|  | 3.3 | High | User | add comment to the book I viewed | I can present my views regarding it in public | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a comment section below the book description. • Present all the views and thoughts regarding that book in the section. • Click the add button to add the comment and make it publicly visible.
|  | 3.4 | High | User | give rating for a book I viewed | I can express my reactions towards it | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a rating bar next to the comment section below the book description. • Express the reaction towards that book by rating it via that rating bar. • After rating it will be publicly visible.
|  | 3.5 | Medium | User | add a book to favourites | I can view it later | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Add to Favourites' button next to the book image. • Click the button to add book to favourites. • Browse the favourites section to see the added book as favourites.
|  | 3.6 | Low | User | share a book in other social platforms | user of other social medias can also view it | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Share' button next to the 'Add to Favourites' button. • Click the button to access the modal with hyperlink of the book. • Copy the hyperlink and share it in other social medias.
F4 | Searching | 4.1 | Medium | User | search for a book of my choice | I can know about it in more detail | • Add a search button in the navigation bar of the system. • Provide the search tag of interested book (date of publish, genre, name, etc.) and click the search button. • Display the relevant data based upon the search filter provided and go through it.
F5 | Booking | 5.1 | High | User | buy a book of my choice | I can read it | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a buy button next to the add comment button. • Click the button to initate the purchase. • Select the desired payment method and continue to pay.

## User Story Priority Hierarchy
AGILE USER STORY - HIERARCHY
Feature ID | User Story Id | Priority | As a <Type of user> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria
F1 | 1.1 | High | User | register to the system by creating an account | use the system. | • Add register button in the navigation bar of the system. • Display the registration form when the button is clicked. • Provide all the required fields with proper validation. • Finally, click the register button placed in the form for creating the account.
F1 | 1.2 | High | User | be notified via an email verification mail to my email address | I can verify my account after registration. | • Send an email verification link to registered email address of the user. • Click the verification link attached with email for account verification. • Verification link expires after 24 hours. • Once verified link cannot be reused.
F1 | 1.3 | High | User | login to the system after registration | I can access the system | • Add a login button in the navigation bar of the system. • Display the login form when the button is clicked. • Provide login credentials to the required fields with validation. • Ultimately, click the login button for accessing the system. • Display the dashboard page after successful login.
F1 | 1.5 | High | User | reset my password | I can create a new one to access the system | • Add a forget password button on login page. • Click the placed button. • Display the form for resetting the password. • Accept valid and registered email of user in the form and submit it. • Send a password reset link to the provided email address. • Click the reset link attached with email for resetting the password. • Access the password reset form in the browser and provide the new password. • Ultimately, click the button placed in the form for resetting the password with the new one. • Reset link expires after 24 hours. • Once verified link cannot be reused.
F2 | 2.3 | High | User | add a book to the system | other users can go through it and carryout relevant activities | • Add 'Upload a Book' link on navigation bar of the dashboard. • Click the link to access the upload a book form. • Ask for various details of book to upload with proper validation. • Click the 'Add' button placed in the form for adding book to the system. • Redirect to the 'MyBooks' section after adding book successfully.
F2 | 2.4 | High | User | review my books | I can see its booking transactions and other information | • Access and go through the 'MyBooks' section in the dashboard. • Display all the books hosted by a user. • Click on a book to view its booking details, reviews and ratings. • Review the information to perform various activites.
F2 | 2.5 | High | User | update the details of book I uploaded | other users can view latest information regarding it | • Access and go through the 'MyBooks' section in the dashboard. • Display all the books hosted by a user. • Click on a book to update and access the update form. • Provide new information and click the 'Update' button to update the book.
F3 | 3.1 | High | User | explore the various kinds of available books | I can look for the one of my choice | • Access the home page of the system where all the books are presented. • Display a section in the page where the information about various books are presented and updated. • Select and go through the section for viewing the information presented about various books. • Compare the presented information of various books with each other.
F3 | 3.2 | High | User | view a book of my choice in detail | I can figure out its price, writer, comments, ratings and other detailed information | • Access the home page of the system where all the information is presented. • Display a section in the page where the information about various books are presented and updated. • Select and go through the section to view the information presented about different books or search the book of choice using the search box placed in the navigation bar by providing essential search filters. • Browse the book of choice and go through it. • View the detailed information about the book.
F3 | 3.3 | High | User | add comment to the book I viewed | I can present my views regarding it in public | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a comment section below the book description. • Present all the views and thoughts regarding that book in the section. • Click the add button to add the comment and make it publicly visible.
F3 | 3.4 | High | User | give rating for a book I viewed | I can express my reactions towards it | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a rating bar next to the comment section below the book description. • Express the reaction towards that book by rating it via that rating bar. • After rating it will be publicly visible.
F5 | 5.1 | High | User | buy a book of my choice | I can read it | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a buy button next to the add comment button. • Click the button to initate the purchase. • Select the desired payment method and continue to pay.
F1 | 1.6 | Medium | User | change my password used during login | I can secure my account | • Add change password link on profile section of the user dashboard. • Click the link to access the change password form. • Ask for old password and accept to enter new password with proper validation. • Once the old password is verified the password should change successfully. • Click the button placed in the form for changing the password. • Clear the session of the logged in user after successful password change. • Redirect to the login page for continuing with new password.
F2 | 2.1 | Medium | User | add a profile picture | I could get recognized by other people. | • Add choose profile picture option on the profile section of the dashboard. • Ask to choose the file and browse the file explorer. • Choose the appropriate picture and upload it. • Click the upload button to add the selected image as profile picture.
F3 | 3.5 | Medium | User | add a book to favourites | I can view it later | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Add to Favourites' button next to the book image. • Click the button to add book to favourites. • Browse the favourites section to see the added book as favourites.
F4 | 4.1 | Medium | User | search for a book of my choice | I can know about it in more detail. | • Add a search button in the navigation bar of the system. • Provide the search tag of interested book (date of publish, genre, name, etc.) and click the search button. • Display the relevant data based upon the search filter provided and go through it.
F1 | 1.4 | Low | User | login to the system using third party OAuth | I can access the system securely with a single click. | • Add continue with (Google, Facebook) option in the login form of the system. • Click the relevant option for continuing the system login. • Select the appropriate account to continue with the system. • Click the selected account and login to the system with single click. • Access the system’s user dashboard after successful login. • Sync and monitor user activities via the host account service provider.
F2 | 2.2 | Low | User | see my activity logs in the system | I can track my activities in the system. | • Add a ‘Activity Logs’ link in the navigation bar of the dashboard. • Click the link and browse a new section in the dashboard. • View all the activities done by the logged in user in that section.
F2 | 2.6 | Low | User | deactivate my account | I can safeguard my privacy | • Add account deactivate button in the profile section. • Click the button to disable their account temporarily or permanently. • Once the account is deactivated it should not be visible in the system. • Clear the session of the user after successful account deactivation.
F3 | 3.6 | Low | User | share a book in social platforms | user of other social medias can also view it | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Share' button next to the 'Add to Favourites' button. • Click the button to access the modal with hyperlink of the book. • Copy the hyperlink and share it in other social medias.

## User Story Map Board
Legend : US - User Story
The Backbone | Epic 1 | Epic 2 | Epic 3 | Epic 4 | Epic 5
Flesh on the backbone | User Account | Dashboard | Viewing | Searching | Booking
Sprint / Iteration 1 (02/08/2021 - 08/08/2021) | US 1 - Registration
SEQUENCE | US 2 - Email Verification
Version 1.0 | US 3 - Login
US 4 - Reset Password
Sprint / Iteration 2 (09/08/2021 - 15/08/2021) |  | US 16 - Add a book
Version 2.0 |  |  | US 9 - Explore the list of books
US 11 - View a book of choice
US 15 - Add book to favourites
Sprint / Iteration 3 (16/08/2021 - 22/08/2021) |  |  |  | US 10 - Search for a book
Version 3.0 |  |  |  |  | US 14 - Buy a book
US 12 - Add comment
US 13 - Give rating
Sprint / Iteration 4 (23/08/2021 - 29/08/2021) |  | US 7 - Activity logs
Version 4.0 |  | US 6 - Add Profile Picture
US 17 - Reviewing book added
US 18 - Update book
Sprint / Iteration 5 (30/08/2021 - 05/09/2021) | US 8 - OAuth login
Version 5.0 | US 5 - Change Password
US 19 - Deactivate account
US 20 - Share a book
RELEASE THEME: Online Book Store (MyPalBooks)

## Agile Release Plan
AGILE RELEASE PLAN
AT RISK | SPRINT | USER STORY NAME | FEATURE TYPE | START | FINISH | DURATION (In Hours) | STORY POINTS | STATUS | RELEASE DATE
| 1 | User Story 1 - Registration | Functionality | 2021-08-02 | 2021-08-04 | 12 | 2 | Planned
| 1 | User Story 2 - Email Verification | Functionality | 2021-08-03 | 2021-08-04 | 6 | 1 | Planned
| 1 | User Story 3 - Login | Functionality | 2021-08-04 | 2021-08-05 | 12 | 2 | Planned
| 1 | User Story 4 - Reset Password | Functionality | 2021-08-04 | 2021-08-06 | 12 | 2 | Planned | 2021-08-08
| 2 | User Story 16 - Add a book | Functionality | 2021-08-09 | 2021-08-11 | 12 | 2 | Planned
| 2 | User Story 9 - Explore the list of books | Functionality | 2021-08-10 | 2021-08-11 | 6 | 1 | Planned
| 2 | User Story 11 - View a book of choice | Functionality | 2021-08-11 | 2021-08-12 | 6 | 1 | Planned
| 2 | User Story 15 - Add book to favourites | Functionality | 2021-08-12 | 2021-08-13 | 6 | 1 | Planned | 2021-08-15
| 3 | User Story 10 - Search for a book | Functionality | 2021-08-16 | 2021-08-17 | 6 | 1 | Planned
| 3 | User Story 14 - Buy a book | Functionality | 2021-08-16 | 2021-08-18 | 12 | 2 | Planned
| 3 | User Story 12 - Add comment | Functionality | 2021-08-18 | 2021-08-19 | 6 | 1 | Planned
| 3 | User Story 13 - Give rating | Functionality | 2021-08-19 | 2021-08-20 | 6 | 1 | Planned | 2021-08-22
| 4 | User Story 7 - Activity logs | Functionality | 2021-08-23 | 2021-08-26 | 18 | 3 | Planned
| 4 | User Story 6 - Add Profile Picture | Functionality | 2021-08-23 | 2021-08-24 | 6 | 1 | Planned
| 4 | User Story 17 - Reviewing book added | Functionality | 2021-08-24 | 2021-08-25 | 6 | 1 | Planned
| 4 | User Story 18 - Update book | Functionality | 2021-08-25 | 2021-08-27 | 12 | 2 | Planned | 2021-08-29
| 5 | User Story 8 - OAuth login | Functionality | 2021-08-30 | 2021-08-31 | 12 | 2 | Planned
| 5 | User Story 5 - Change Password | Functionality | 2021-09-01 | 2021-09-02 | 12 | 2 | Planned
| 5 | User Story 19 - Deactivate account | Functionality | 2021-09-02 | 2021-09-03 | 12 | 2 | Planned
| 5 | User Story 20 - Share a book | Functionality | 2021-09-03 | 2021-09-03 | 6 | 1 | Planned | 2021-09-05

## Agile Sprint 1 Backlog
AGILE SPRINT 1 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 : Registration | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2 | 2 | 1 | 0 | 0 | 0 | 3
Frontend development (Design) |  | Hari Acharya | Planned | 4 | 4 | 2 | 0 | 0 | 0 | 6
TDD Testing |  | Bishnu Adhikari | Planned | 1 | 0 | 1 | 1 | 0 | 0 | 2
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4 | 0 | 2 | 2 | 3 | 0 | 7
BDD Testing |  | Shrawan Thapa | Planned | 1 | 0 | 0 | 0 | 0 | 2 | 2
User Story #2 : Email Verification | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2 | 1 | 0 | 0 | 0 | 0 | 1
Frontend development (Design) |  | Hari Acharya | Planned | 1 | 0 | 1 | 0 | 0 | 0 | 1
TDD Testing |  | Bishnu Adhikari | Planned | 0.5 | 0 | 0 | 1 | 0 | 0 | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 2 | 0 | 0 | 0 | 1 | 0 | 1
BDD Testing |  | Shrawan Thapa | Planned | 0.5 | 0 | 0 | 0 | 0 | 1 | 1
User Story #3 : Login | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2 | 1 | 0 | 0 | 0 | 0 | 1
Frontend development (Design) |  | Hari Acharya | Planned | 4 | 2 | 0 | 0 | 0 | 0 | 2
TDD Testing |  | Bishnu Adhikari | Planned | 1 | 0 | 0 | 0.5 | 0 | 0 | 0.5
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4 | 0 | 2 | 2 | 3 | 0 | 7
BDD Testing |  | Shrawan Thapa | Planned | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #4 : Reset Password | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2 | 1 | 0 | 0 | 0 | 0 | 1
Frontend development (Design) |  | Hari Acharya | Planned | 4 | 2 | 0 | 0 | 0 | 0 | 2
TDD Testing |  | Bishnu Adhikari | Planned | 1 | 0 | 0 | 0.5 | 0 | 0 | 0.5
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4 | 0 | 2 | 2 | 3 | 0 | 7
BDD Testing |  | Shrawan Thapa | Planned | 1 | 0 | 0 | 0 | 0 | 1 | 1
TOTAL |  |  |  | 42 | 13 | 11 | 9 | 10 | 5 | 48
IDEAL |  |  |  | 42 | 4.6 | 2.6 | 0.6 | 1.6 | -3.4 | 48

## Agile Sprint 2 Backlog
AGILE SPRINT 2 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #16 : Add a book | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2
Frontend development (Design) |  | Hari Acharya | Planned | 4
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #9 : Explore the list of books | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 2
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 1
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #11 : View a book of choice | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 2
TDD Testing |  | Bishnu Adhikari | Planned | 0.5
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 2
BDD Testing |  | Shrawan Thapa | Planned | 0.5
User Story #15 : Add book to favourites | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 1
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 2
BDD Testing |  | Shrawan Thapa | Planned | 1
TOTAL |  |  |  | 30
IDEAL

## Agile Sprint 3 Backlog
AGILE SPRINT 3 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #10 : Search for a book | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2
Frontend development (Design) |  | Hari Acharya | Planned | 4
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #14 : Buy a book | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 4
Frontend development (Design) |  | Hari Acharya | Planned | 3
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 3
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #12 : Add Comment | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 1
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 2
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #13 : Give rating | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 1
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 2
BDD Testing |  | Shrawan Thapa | Planned | 1
TOTAL |  |  |  | 30
IDEAL

## Agile Sprint 4 Backlog
AGILE SPRINT 4 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #7 : Activity logs | 3 |  | Planned | 18
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 4
Frontend development (Design) |  | Hari Acharya | Planned | 6
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 6
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #6 : Add Profile Picture | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2
Frontend development (Design) |  | Hari Acharya | Planned | 1
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 1
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #17 : Reviewing book added | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 2
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 1
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #18 : Update book | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2
Frontend development (Design) |  | Hari Acharya | Planned | 4
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4
BDD Testing |  | Shrawan Thapa | Planned | 1
TOTAL |  |  |  | 42
IDEAL

## Agile Sprint 5 Backlog
AGILE SPRINT 5 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #8 : OAuth login | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2
Frontend development (Design) |  | Hari Acharya | Planned | 4
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #5 : Change Password | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 3
Frontend development (Design) |  | Hari Acharya | Planned | 3
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #19 : Deactivate account | 2 |  | Planned | 12
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 2
Frontend development (Design) |  | Hari Acharya | Planned | 4
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 4
BDD Testing |  | Shrawan Thapa | Planned | 1
User Story #20 : Share a book | 1 |  | Planned | 6
Backend development (Database & API) |  | Prajjwol Upadhayaya | Planned | 1
Frontend development (Design) |  | Hari Acharya | Planned | 2
TDD Testing |  | Bishnu Adhikari | Planned | 1
Frontend Development (REDUX implementation & API) |  | Ram Khatri | Planned | 1
BDD Testing |  | Shrawan Thapa | Planned | 1
TOTAL |  |  |  | 42
IDEAL